## Project Planner
Project Planner
Select a period to highlight at right. |  |  |  | Period: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete
ACTIVITY | PLAN START | PLAN DURATION | COMPLETION DATE | PERCENT COMPLETE | PERIODS
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Read TweetEval material | 1 | 1 | 1 | 100%
Read surrounding literature | 1 | 1 | 1 | 100%
Download, build, & stage TweetEval | 1 | 1 | 1 | 100%
Load & explore data | 2 | 1 | 2 | 100%
Implement preprocessing tasks | 2 | 4 |  | 25%
Download, build, & stage NLTK | 3 | 4 |  | 25%
Implement prepro. NLTK methods | 3 | 5 |  | 25%
Implement POS tagging | 8 | 4 |  | 0%
Implement Chunk phrasing (all) | 11 | 5 |  | 0%
Named-entity recognition | 14 | 5 |  | 0%
Code integration | 6 | 17 |  | 0%
Code cleanup, review, and doc. | 20 | 2 |  | 0%
Setup training process for ML | 17 | 5 |  | 0%
Setup benchmarking & testing for LM | 19 | 4 |  | 0%
Results gathering & presentation | 23 | 3 |  | 0%
Final report writing | 22 | 10 |  | 0%